## Sheet1
The Lady Production Schedule	December / **Milestone**	January / **Milestone/IndieGoGo**	February / **Alpha**	March / **Alpha**	April / **Beta/Final**	May / **Release**	June / **Late Release**
Priorities for the month	(aside from completing preparation with your engine)The biggest priority this month should be blocking out level 1 for milestone builds, so we can assess how long it might take to build the other levels, as well as finishing up Spriter integration. I'm not going to feel comfortable putting up the IndieGoGo without at least one level near or at completion. / Level 1 animations should be completed this month, there's not many in this level. / For me, writing up a solid IndieGoGo Campaign, to be ready to publish by mid January. Continue Promo Push. / **Start on Title Screen**	• Level's 2,3, and 5 "maze" functionality / • Assess any obstacles that might come with the maze functionality / • Finalize Level 1 / • Block out level 2 & 3 / • Experiment with Boss Battles / • Animations for level 2-5 worked on / For me, Finalize the IndieGoGo Campaign, publish, and promote the IndieGoGo Campaign. Manage and assess artistic direction progress, start on music if not already in place. / **Explore distribution possibilities**	• Levels 4 and 5 blocked out and taken to near completion if not completion. / • Finalize level 1-3 / • Boss Battles , assess if they fit in, how many we should keep / For me, MUSIC and SFX if not already completed by this point. / **Continue to explore distribution possibilities**	**I'm writing this block assuming you're out on surgery recovery this month** / • All levels are finalized / • Testing, lots of testing / For me, all distribution possibilities are contacted and at least 2-4 are in place for the game by this point. Finalize the soundtrack and SFX. / Continue Promo Push.	Make any last minute fixes, changes, etc.	Sell the game, making money getting cash getting paid$$ / HUGE promo push. / Follow up with all previous promo outlets.	If we've made it this far we've hit "late release" / :(
End of the Month Expectations	• Level 1 blocked out or near completion with or without placeholders. / • Spriter integration complete / • Animations for Level 1 are completed / • 4-6 very short pseudo gameplay videos for the IndieGoGo video / • A playable build of Level 1	• Level 1 & 2 completed / • Boss Battles blocked out / • A playable build of level's 1,2, and 3 / • Animations for levels 2 are completed / • Animations for level 3-5 are near complete / • IndieGoGo is published by early-mid January $$$$$	• All levels blocked out or near completion / • A Title Screen is in place / • Playable builds of all levels / • All Animations for the game are completed / • IndieGoGo is over, $$$ is split up	• All levels are completed and playable for QA testing / • Music and SFX completed and in game / • Title screen is complete and menu navigation is being tested / • Distribution is in place	• The final build is delivered and solid to pass QA for release to the public	Release a piece of art, and turn heads in the gaming world, while making some $$	Huge loss of $$ for me
Roger's Concerns and Comments			This month would probably also be the cutoff point for trying out any new visual effects	While I'm recovering, I recommend getting a lot of people to play the alpha and the beta to help maximize compatibility on release – likely we'll have compatibility-related bugs to fix after release
My Concerns & Comments	My only concern right now is that level one has not begun to be blocked out with the provided placeholder art.